## Sheet1
Risk ID | Risk Description | Threat Source | Asset Impacted | Likelihood | Impact | Risk Score | Risk Treatment Strategy | Proposed Controls | Residual Risk
R7 | Outdated (not updated) market news with incorrect gold rates, leading to false buy from customers and hence facing huge loss and financial fines | Third Party Provider | Intellectual | 4 | 4 | 16 | Mitigate | 1. Technical Control Implemented, such that if the gold rate is not updated within 30 sec, the Buy option is disabled, thus preventing false buy 2. Administrative Control Implemented, such that a SLA of 99.9% is decided with the market feed provider for data refresh. | Medium
R4 | An employee who has left the firm still has access to Admin portal leading to downloading PII data of employee and selling them | Disgruntled Employee | Data | 3 | 5 | 15 | Mitigate | 1. Automation to revoke admin access within 15 minutes of termination. Also Check every week if employee is part of the firm or not and basis update Admin portal access 2. Implement a 2- face authentication for accessing and downloading PII 3. Tool that flags bulk export of PII | Medium
R5 | AWS Lambda cold start due to which customers missing the initial purchase , leading to lots of fines and losses | Data Flow | Infrastructure | 3 | 4 | 12 | Mitigate | 1. Automate AWS Lambda 10 minutes prior to market open to prevent cold start 2. Implement a Multi-Region Failover. Set up an internal SLA of 0.1 seconds so that If AWS Lambda is slow (less than SLA) for a region it automatically transfers the connection / traffic to another region who is active and responding | Medium
R3 | A disgruntled employee has access to Admin panel leading to deleting the AWS lambda service | Disgruntled Employee | Data | 3 | 4 | 12 | Mitigate | 1. Implement a mutliface access to Admin panel. Configure the AWS environment so that a "Delete" command requires two separate people to approve it in the console before it executes. 2. Automate a trigger using AWS CloudTrail whenever there is any editable action performed on AWS lambda service. 3. Have a multi-region backup of the service, in case of any disaster | Low
R10 | Corrupt authentication in the API Gateway leading to a cyber-attack. Huge financial loss and fines imposed | Data Flow | Infrastructure | 2 | 5 | 10 | Mitigate | 1. Implement multi factor authentication and Centralized Identity management (with short lived tokens) for all authentication for API Gateway 2. Have a multi-region backup of the service, such that in case of a cyber attack, we can shut this service and switch over to the backup environment. For the important service, establish a warm site 3. Implement an automated notification trigger (via AWS Cloud Watch) in case of spike in the malicious IP address search or “401 Unauthorized error” | Low
R2 | A employee who has left the firm, has created a back door entry leading to deleting the data base | Disgruntled Employee | Data | 2 | 5 | 10 | Mitigate | 1. Automated trigger of revoking access to all the employees who has left the firm within 15 minutes 2. Multifactor authentication before confirmation of any editable action on database. Role based access control and Privilege Action Management 3. Conduct Quarterly User Access Review (UAR) and Regular pen testing to identify any backdoor entries or unauthorized access. | Low
R1 | A disgruntled employee has access to Github repository, leading them to stealing 0.01$ from every account everyday | Disgruntled Employee | Financial | 2 | 4 | 8 | Accept
R6 | Third party payment lines broken, leading to customers facing payment declined request, after amount is deducted from their account | Third Party Provider | Financial | 2 | 4 | 8 | Accept
R8 | KYC platform down, leading to customers facing login issues and have to redo the KYC | Third Party Provider | Financial | 2 | 4 | 8 | Accept
R9 | Malicious code inserted in the AWS Lambda service, leading to downtime for the platform, hence inconvenience for the customers as well as financial loss | Data Flow | Infrastructure | 2 | 4 | 8 | Accept